## Sheet1
Item | % of Total | Cumulative % | Enter 1 if Complete | CIP
Excavation | 2 | 2 | 1 | 2
Forms set | 2 | 4 | 1 | 2
Foundation and/or blocks | 8 | 12 | 1 | 8
Basement floor | 2.5 | 14.5 | 1 | 2.5
Joists set | 2 | 16.5 | 1 | 2
Subfloor | 2 | 18.5 | 1 | 2
Framed | 7 | 25.5 | 1 | 7
Sheathed | 5 | 30.5 | 1 | 5
Roof installed | 4 | 34.5 | 1 | 4
Windows set | 4 | 38.5 | 1 | 4
Siding on | 5 | 43.5 | 1 | 5
Heating installed | 6 | 49.5 | 1 | 6
Plumbing roughed in | 6 | 55.5 | 1 | 6
Wiring roughed in | 3 | 58.5 | 1 | 3
Insulated | 2.5 | 61 | 1 | 2.5
Walls roughed in | 2 | 63 | 1 | 2
Walls finished | 5 | 68 | 1 | 5
Interior trim & cabinets | 6 | 74 | 1 | 6
Doors hung | 2 | 76 | 1 | 2
Wiring finished | 3 | 79 | 1 | 3
Plumbing fixtures in | 3 | 82 | 1 | 3
Floors finished | 5 | 87 | 1 | 5
Finished hardware | 1 | 88 | 1 | 1
Interior decorated | 4 | 92 | 1 | 4
Outside painted | 3 | 95 | 1 | 3
Water and sewer connected | 2 | 97 | 1 | 2
Exterior concrete work | 3 | 100 | 1 | 3
Total | 100 |  | Total CIP | 100